## Pipeline Trends
Kismet Finance — Pipeline Trends (Feb 20 – Apr 2, 2026)
Source: DQ Status Tally (cumulative daily snapshots). All figures = pipeline state on that date.
Consultant | Feb 20 Pipeline | Apr 2 Pipeline | Change | Growth % | Trend Note
Josh (Coach) | 65 | 58 | -7 | -10.77% | Mature — leads cycling to Shane for closing
DJ (Door-knocker) | 0 | 58 | 58 | New | Surging — 0→58 in 5 weeks, matched Josh
Lea (Door-knocker) | 26 | 28 | 2 | 7.692% | Frozen — static 15+ days, departing
Shane (Closer) | 1 | 13 | 12 | 1200% | Small but growing; closes off-system
TOTAL | 92 | 157 | 65 | 70.65% | Pipeline growing — driven by DJ onboarding
Pipeline Composition — Apr 2, 2026 Snapshot
Consultant | Total Leads | Warm Leads | Discovery+ | Sale Stage | Rejection %
Josh (Coach) | 58 | 20 | Multiple | Data entry only | 36%
DJ (Door-knocker) | 58 | 20 | 2 (FA on Apr 2) | None yet | 32%
Lea (Door-knocker) | 28 | 8 | Some | None | 40%
Shane (Closer) | 13 | 3 | Some | Closes off-Notion | 42%
TOTAL | 157 | 51 | — | Shane closes; Josh records | 37.5%

## Rejection Trend
Rejection Rate Trend Analysis
Within-snapshot ratios — valid metric. Rejection = Fake Number + Not Interested + Future Prospects + DNQ.
Period | Rejection Rate | Change vs Baseline | Interpretation
Late Feb (Feb 20–23) | 16% | 0% | Baseline — healthy, ~1 in 6 rejected
Early Mar (Feb 24 – Mar 10) | 30% | 14% | Sharp jump — lead quality shift or territory exhaustion beginning
Late Mar (Mar 20–31) | 45% | 29% | Peak — nearly half rejected. Josh notes 'warm leads cooling across board'
Early Apr (Apr 1–2) | 39% | 23% | Slight improvement but still 2.5x baseline. Structural or seasonal?
Possible Root Causes (requires investigation)
Hypothesis | Likelihood | Investigation Needed
Territory Exhaustion | HIGH | Same suburbs re-canvassed; declining fresh leads. Territory management system (Phase 3) not built yet.
Seasonal Effect | MEDIUM | Mar–Apr may see lower receptivity. Need historical comparison (no prior data available).
Categorisation Drift | MEDIUM | Has the definition of 'rejection' changed? Are door-knockers categorising differently over time?
Door-knock Quality | LOW-MED | DJ is new; Lea is disengaged. Could be declining technique. Josh's coaching should counteract this.

## Areas for Improvement
Kismet Finance — Key Areas for Improvement
Prioritised by impact × urgency. Status as of April 7, 2026.
Area | Priority | Owner | Timeline | Detail / Action Required
Shane's CRM Adoption | CRITICAL | Shane + Kevin | Week 1 | Shane closes deals off-Notion. Sales are invisible to the system. Build a Fillout form → Notion push to minimise friction. Even 5 min/day logging deal stages unlocks close-rate measurement.
Lea's Lead Redistribution | CRITICAL | Josh | Day 1 | 28 leads frozen 15+ days. Every day = further decay. Reassign to DJ by territory. 1-day admin task with immediate value preservation.
Financial Data (P&L / Revenue) | CRITICAL | Josh + Kevin | Weeks 1–4 | All financial templates blank ($0). Cannot verify ROI, substantiate grants, or measure revenue. Populate from Shane's actual closed deals.
Rejection Rate (39%, was 16%) | HIGH | Josh + Kevin | Weeks 3–6 | 2.5x baseline. Analyse DQ snapshots for territory exhaustion patterns. Build territory management system (Phase 3). Deploy voice agent as alternative channel.
DJ → Handoff Quality | HIGH | Josh | Weeks 2–4 | DJ ramping fast (0→58) but needs to qualify leads to handoff-ready for Shane. FA conversions on Apr 2 are promising. 3x/week coaching sessions with Josh.
Phase 3 Delivery (0%) | MEDIUM | Kevin | Weeks 3–12 | 50+ tasks at 0%. Prioritise: territory management, mobile field forms, Ghost Detector. Don't gate on grant — start highest-impact items.
Phase 1 Overdue Items | MEDIUM | Kevin | Weeks 2–6 | Phase 1 end date was Jan 2026. AI training data repo, rollup fields, GCP/Vertex AI still open. Close these before scaling Phase 3.
Grant Application (LCF) | MEDIUM | Kevin + Shane | Weeks 6–12 | Up to $50k at 50% match. Need: populated financial data, DQ baseline KPIs, Phase 3 project plan. Round 2 timing uncertain.
Lea Replacement / Recruitment | LOW-MED | Shane + Josh | Weeks 4–8 | Door-knock capacity drops when Lea leaves. DJ can absorb some but is part-time (uni). Consider recruiting another uni student.
Resale Pipeline (Stuart et al) | LOW | Shane + Kevin | Weeks 8–12 | Voice agent resale to Stuart, property devs, brokers ($12k–$35k/yr potential). Don't pursue until internal system is stable.
Quick Scorecard
Metric | Value | Context | Status
Pipeline Growth | +47% | 107 → 157 in 6 weeks | POSITIVE
Rejection Rate | 39% | Up from 16% baseline (2.5x) | NEGATIVE
CRM Data Completeness | ~60% | Shane's sales activity missing entirely | NEGATIVE
Financial Data | 0% | All templates blank — no revenue accounting | CRITICAL
Phase 3 Progress | 0% | 50+ tasks not started | BEHIND
DJ Ramp | On track | 0→58 leads, FA conversion started | POSITIVE
Single Closer Risk | HIGH | Shane = only closer, off-system | NEGATIVE