## Table 1
Module/Task Name | Primary Goal | Tool or Platform | Responsible Party | Status | Success Metric | Priority/Phase | Source
CEO Claude Project Command Center | Establish a strategic command center for operational awareness and task dispatching. | Claude.ai Project | Kev | Phase 1 - In Progress | Operational awareness achieved in < 30 seconds of opening session. | Phase 1 / Immediate Setup | 1, 2
Obsidian IDE Configuration | Configure Obsidian as a unified workspace/IDE where projects and CLI agents operate. | Obsidian (Local-first) | Kev | Phase 3 - Not Done Yet | REST API accessible from n8n; projects folder moved into vault root. | Phase 3 / Immediate Setup | 1, 2
Notion Cleanup & Shared State Setup | Clean legacy noise and establish shared state registry for clients and actioners. | Notion | Kev / Claude | In Progress (Partially Organized) | No orphaned pages; Client select includes Lee Monarc; Task board views functional. | Phase 4 / Immediate Setup | 1, 3
n8n Automation Workflows | Deploy recurring automations for session logging and daily task digests. | n8n (NAS-hosted) | Kev / n8n AI Agent | Phase 5 - Not Done Yet | At least 2 automations (session log + daily digest) running 24/7. | Phase 5 / Immediate Setup | 1
Research Pipeline Connection | Connect Perplexity, NotebookLM, and Gemini for structured research extraction. | Perplexity / NotebookLM / Gemini CLI | Good AI Analyst (Gem) | Phase 6 - Not Done Yet | Tested end-to-end with one real topic; structured JSON output achieved. | Phase 6 / Strategic Roadmap | 1, 2, 4
MVP Development - Core Strategy Modules | Build modules 1-3: Brand Purpose, Competitive Positioning, and Personality Assessment. | React.js / Node.js / Figma | Builder/Developer Agent | Planned | 60% completion rate for Module 1 among beta users. | Phase 1 (Months 1-6) / Product Roadmap | 5, 6
Market Research & Competitive Analysis | Conduct 50+ interviews and map landscape to validate PRD assumptions. | SEMrush / Hotjar / Typeform | Research Analyst Agent | Planned | 70% of interviewed users confirm the core problem statement. | Phase 1 (Months 1-4) / Product Roadmap | 5, 7
Advanced Visual Identity Development | Implement modules 4-8 including AI color psychology and typography pairing. | Google Stitch / Figma Make | Brand/Creative Director Agent | Planned | Generated color palettes achieve 90% accessibility compliance. | Phase 2 (Months 7-12) / Product Roadmap | 5, 6
Brand Guidelines Generation System | Automate professional brand guidelines PDF generation and multi-format asset export. | Google Opal / Figma Buzz | Ops Manager / Builder Agent | Planned | Preview engine renders mockups within 3 seconds. | Phase 2 (Months 7-12) / Product Roadmap | 5, 6
AI Recommendation Engine Enhancement | Train machine learning models on successful brand case studies for strategy reasoning. | Google AI Studio / Vertex AI | Strategy / Developer Agent | Planned | Typography recommendations receive 4.2+ star ratings. | Phase 3 (Months 13-18) / Product Roadmap | 5, 6

## Source references
Index | Reference
1 | 2026-03-28-good-ai-master-plan-v1.md
2 | GOOD-AI-CEO-SYSTEM-PROMPT-v2.md
3 | GOOD-AI-PROJECT-PLAN.md
4 | GEMINI-GEM-RESEARCH-ANALYST-v2.md
5 | Comprehensive Ideation to Deployment Roadmap_ Bran.pdf
6 | Product Requirements Document_ Brand Strategy & Id.md
7 | Comprehensive Ideation to Deployment Roadmap_ Bran.pdf